## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Tester | 2025-10-06 | Missing values not handled in data collection | Sprint 1 | Backend Team | Data Issue | Added null-handling logic | 2025-10-07 | Closed | Fixed successfully
2 | Data Scientist | 2025-10-15 | Wrong scaling applied on income column | Sprint 2 | DS Team | Preprocessing Error | Corrected scaling function | 2025-10-16 | Closed | Verified
3 | Tester | 2025-10-30 | Feature mismatch between train & predict | Sprint 3 | DS Team | Feature Engineering Issue | Pending fix | 2025-11-02 | Open | Under investigation
4 | Developer | 2025-11-04 | UI input validation missing | Sprint 4 | Backend Team | UI Bug | Validation rules to be added | 2025-11-05 | Open | Will update next sprint
5 | Tester | 2025-11-10 | Flask API returns incorrect response on empty fields | Sprint 5 | Backend Team | API Logic Issue | Fix in progress | 2025-11-11 | Open | Needs logic update

## Sheet2
Logical
User Interface
Maintainability
Standards
Others